Program Name:	Navigating Pacific Hearts

Project Description:

"Navigating Pacific Hearts" will engage Native Hawaiian and Other Pacific Islander (NHPI) women in Orange and Riverside Counties, California in the Heart Truth campaign to provide skills necessary for recognizing and reducing heart disease risk. Pacific Islander Health Partnership (PIHP) and UCR's Center for Healthy Communities (CHC) will collaborate with seven NHPI community organizations in a broad outreach programing at Pacific Islander Festivals and the implementation of the PILI 'Ohana program that teaches cooking with traditional foods, weight management and increasing physical activity. Twelve outreach workers will be trained to facilitate the proposed programs for NHPI women.

PROGRAM OBJECTIVES:

Objectives for broad public awareness include:

- Use Heart Truth educational materials and outreach to increase knowledge of heart disease risk factors and risk reduction for NHPI Women

- Increase NHPI women's ability to engage in heart health conversations with their physician

- Adapt educational and training materials for five NHPI groups by modifying the Kaleponi PILI 'Ohana Program (KPO).

- Design and host a special event for American Heart Month

Objectives for community-level engagement include:

- Use the existing infrastructure of PIHP to build an NHPI community Heart Health collaborative of women volunteer leaders to include Native Hawaiian, Samoan, Tongan, Marshallese, Chamorro community organizations of civic clubs, social-cultural-family, faith-based, athletic, and small businesses.

- Train at least two heart healthy trainers from each of the NHPI community partners

- Engage community partners in the development and production of NHPI language appropriate Heart Healthy materials.

TARGET POPULATION:

Our program is focused on the heart health needs of Native Hawaiian and Other Pacific Islander (NHPI) adult women. Pacific Islander health programs are most effective when they are intergenerational and family oriented (McMullin et al 2010). Therefore, our secondary target population are the family members of the women participating in our programing.

TARGET GEOGRAPHIC AREA:

California has the largest population (282,000) of NHPI in the United States (US Census 2010), with the number now surpassing the NHPI population of Hawaii. More than 22,000 live in Orange and Riverside Counties. Despite their rapid population growth the needs of NHPI have been obscured because of the historical aggregation of their data with Asian

Americans. As one community member told us, "we [Pacific Islanders] are the invisible population." When we consider Panapasa et. al (2010) findings that Native Hawaiians 65 and older have the highest mortality rates in the United States, higher than African Americans, that heart disease is the leading cause of death (34%) for NHPI, and that in Orange County with 42% of the Native Hawaiians, 24% of Guamanian or Chamorro and 28% of Samoan deaths attributable to heart disease (Community Contrasts 2014) we can no longer afford to ignore the health needs of NHPI.

DESCRIBE THE ACTIVITIES THAT YOU WILL UNDERTAKE TO BUILD BROAD PUBLIC AWARENESS OF HEART DISEASE AND WOMEN AND THE HEATH TRUTH PROGRAM.

Faculty at the UCR CHC are well-versed in the principles of community-participatory work, including the Citizen Health Care model. Based on these models a key emphasis for our project is the belief that families and communities are producers of the solutions to health care issues. We will begin during the first month of the project. We will create a steering committee consisting of one representative from each of the NHPI community partners, and co-lead by Ka`alakahikina (Ka`ala) Pang, RN, PHN and Program Manager for PIHP, and Juliet McMullin Project Director and faculty at UCR's CHC. We will also hire a Project Program Manager to assist in coordinating all activities. The SC will oversee all project activities, provide support and feedback on the development of NHPI Heart Health materials and the implementation of the KPO program. The key activity in our broader public awareness activities will be our education, outreach and evaluation of heart truth materials at Pacific Islander festivals.

NHPI festivals. Our first education and outreach event will occur in July at the two-day 37th Annual Ho'olaule'a Festival attended by about 100,000 people every year. We will host a booth at the event where we will distribute current Heart Truth educational materials. We will conduct informal interviews with at least 50 women and focus on what materials that emphasize NHPI values should include in order to be more effective in its health messaging. We will also advertise the KPO program scheduled to begin in October (see activating local partners for more information on KPO). Results of interviews from the Ho'olaule'a will be used to discuss with our SC about how they would like to adapt the educational materials for their community. We will then proceed to develop Heart Truths to address major risks for heart disease to translate in Pacific Islander languages for flyers, cards, posters, social media for community wide distribution. These materials will be distributed at the 8th Annual Pacific Islander Festival in September in Huntington Beach, CA. (10,000 attendees), at the 3rd Annual Pacific Islander Holiday Festival, Fountain Valley (2,000 attendees) in November of 2015, and at the 4th Annual Ho'olaulea (10,000 attendees), Beaumont in May of 2016.

We will kick off the second six months of our program with a community gathering to highlight American Heart Month. Our community partners and broader public will be invited to a gathering where we will share the work of each community partner,and strategize our next steps for greater public awareness of women's heart health. We will create a curated display of the artwork, stories (see community descriptions), and all Heart Truth material created by our community partners. We will end the event with a red dress fashion show tentatively titled Lehua Ula (red Lehua flower -- which is a symbol of strength and power for Native Hawaiians). Each community is responsible for contributing to February's American Heart Month event, both in reporting their activities and participating in the Pacific Island fashion show celebrating thriving survivors of heart disease.

DESCRIBE HOW YOU WILL DEVELOP, COORDINATE, AND PROVIDE OVERSIGHT OF COMMUNITY- BASED HEART HEALTH ACTIVITIES THROUGH LOCAL PARTNERS.

PIHP is the lead community partner in the collaborative, for over 20 years PIHP has been a leader in bringing together and developing the capacity of NHPI communities to address their health needs in southern California. PIHP is the lead organizer of the Pacific Islander Festival and coordinates the participating community organizations of creating their "Island Villages" at the festival. PHIP has had a collaborative working relationship with Prof. Juliet McMullin for over a decade, working on issues related to nutrition and NHPI community building.

Coordination and oversight:

Consultant, Ualani Ho'opai, has experience working with each of the community partners and is a trainer for the KPO program. She will advise and assist the project director in coordination and oversight of the community activities and train the trainers in heart health activities.

PIHP Program Manager, Ka`alakahikina (Ka`ala) Pang, RN, PHN, retired has 39 years of extensive clinical experience in clinical cardiac rehabilitation and case management with Los Angeles County; trained as Ulu Network Certified, University of Hawai`i, Mānoa in Heart 101, and KPO trainer will provide support along with the Project Director.

Our first SC meeting with our community partners is designed to strategize the development of programming around their organizations plans for Heart Truth. In addition, to the translation and creation of new NHPI heart health materials, some possible programs could include Pacific dance, outrigger canoe weekends, art, weaving, storytelling or native language instruction.

Month two: We will begin training the trainers in both the Heart Truth educational materials and the KPO program. KPO is a 9-month intervention targeting overweight/obesity in NHPI. The program has two phases. The first phase focuses on weight loss through healthy eating and physical activity. The second phase focuses on weight-loss management through focusing on the family and community support. The KPO program will occur in October-November 2015 (phase 1), and in February-March 2016 (Phase 2). In addition to evaluation measures from the KPO program, we will conduct the pre and post-test The Heart Truth evaluation with additional questions tailored to NHPI.

To insure progress of the community-based activities the SC will:

- Have bi-monthly conversations (by phone or in person) with partners the first and third week of every month.

- Monthly meetings in person meetings of all partners

- Participation at all public activities and process evaluation of and by the community partners

Community contributions at all levels is critical to the success of the program. Their contribution in objective 1 and 2 would be achieved as regular participants and outreach workers at the listed festivals. The initial activity for our community partners is to produce NHPI Heart Truth materials for their own community, thus contributing to objective 3. Our community partners have created a large public with whom to share the Heart Truth materials. Community members will identify individuals who will participate in the train-the-trainer program and recruit women and their families for the KPO program thus contributing to the success of community level objectives 2-3 and public awareness objective 3.

COMMUNITY PARTNERS:

Pacific Islander Health Partnership -Victor Kaiwi and Jane Ka'ala Pang ‘Ainahau o Kaleponi - Charlene Kazner/Ualani Ho`opai

Samoan American Youth of Orange County (SAYOC) -- Toaono Vaifale Famili Pe Taha - Melenaite Fifita/Melevesi Talavou

Juan Wot Iakwe - France Ledbetter (Marshallese Christian Center-Pastor George Briand) Kutturan Chamoru Foundation (KCF) - Heidi Quenga/Joey Quenga

CIHA - CAL-Islanders Humanitarian Association -- Perci Flores/Suzanne Santos

Pacific Islander Health Partnership (PIHP). www.pacifichealthpartners.org will be the primary partner in the project and will assist in facilitating and overseeing community collaborations. The Mission of PIHP is to serve indigenous Hawaiians and Pacific Islanders to educate, advocate, train leaders and build community capacity for health for islanders to reduce health disparities in cancer, diabetes, heart disease, obesity and other chronic illnesses with special programs for island seniors and youth. The core values that motivate and guide PIHP are based on Native Hawaiian values that we share across all island communities. ALOHA: caring, compassion for others, sympathy, love/affection; KOKUA: help, assist, comfort, support; KULEANA: privilege, responsibility, title, job; MALAMA:  caring, nurturing others, to protest, stewardship for land (mālama `āina)

and ocean (mālama ke kai); LOKAHI: unity, agreement, accord, keep in balance with mind, body and spirit; imbalance causing illness and disease; PONO: correct, right, good, moral, fair, proper, just; KU PA`A: stand firm, steadfast, firm, loyal, to strengthen, establish; 'IKE PONO: to know, to feel, to understand, to recognize; HO'OMAU: to preserve, to perpetuate, to continue; HA'AHA'A: humility, humbleness, modesty. PIHP is the lead organizer and supporter of the Annual Pacific Islander Festival in Huntington Beach. This festival just celebrated its seventh year of gathering all Pacific Islanders coming together in California. The networks and resources that PIHP brings to bear on this proposed project will ensure the success of promoting Heart Truth education materials, and the distribution and evaluation of materials at the festivals, and the overall success of the program.

'Ainahau o Kaleponi Hawaiian Civic Club, 'Ainahau o Kaleponi Hawaiian Civic Club, www.aokhcc.org. 'Ainahau O Kaleponi Hawaiian Civic Club is a private, charitable non-profit organization whose primary objective is to practice and perpetuate the traditions, beliefs, language and the arts of the indigenous people of Hawaii. Chartered by the Association of the Hawaiian Civic Clubs in the State of Hawaii in 1982, 'Ainahau provided the leadership for the formation of the Mainland Council of Association of Hawaiian Civic Clubs. As the largest Hawaiian Civic Club in Orange County, 'Ainahau has a broad network of women who could participate in the production of culturally tailored materials. In addition to contributing to the development of Hawaiian language materials, culturally tailored programming, and recruitment to PILI 'Ohana, their emphasis on sharing Na Mea Hawai'i (all things Hawaiian) and regular community service performances make them an ideal partner for developing programs around hula, mele (song) and storytelling. AOKHCC continues to provide over $200,000 in educational and cultural practice scholarships since its inception. 'Āinahau has access to over 100 hula hālau, social, athletic, small businesses throughout Southern California.

Samoan American Youth of Orange County (SAYOC),. No website. SAYOC provides Samoan American Youth with necessary resources for academic success and professional career development while advocating for the importance of culture providing civic focus on voter registration, immigration and citizenship for Samoan community. In addition to contributing to the development of Samoan language materials, culturally tailored programming, and recruitment to PILI 'Ohana, SAYOC provides access to younger, professional women. Demands of family and career often make it difficult for women to attend to their own health needs. With 28% of deaths due to heart disease among Samoans in Orange County it is critical engage women earlier and provide strategies for maintaining heart health during this increasingly demanding time of life. Programming that SAYOC can also engage are creating materials that would address the needs of this generation Samoan women.

Famili Pe Taha, Tongan American Civic Club (FTP),. No website. Established in 2010, Famili Pe Taha has a mission to reach out with Love, Peace, and Hope to educate, empower, and share the Tongan Culture. Community outreach work varies from immigration workshops to healthcare education and navigation. FPT strives to preserve Tongan culture among the American born/raised generations(s). Much of the focus of FPT's work has been around cultural performance, ethnic food preparation, and community backyard gardening. In addition to contributing to the development of Tongan language materials, culturally tailored programming, and recruitment to PILI 'Ohana, their expertise in community gardens and food preparation make them an ideal partner for creating materials that consider the cultural meaning of food as an integral component of heart health. FPT has taken lead for PIHP's MPACT Motivating Pacifika Against Cigarettes & Tobacco, tobacco cessation using social medial campaign.

Juan Wot Iakwe, Marshallese Civic Group,.

A volunteer Marshallese community organization providing cultural, civic engagement, voter registration, immigration, citizenship access for the migrant COFA (Compact of Free Association) community from the Republic of the Marshall Islands (RMI); health education and navigation to healthcare services and Covered California (ACA) enrollment. JWI community of Marshallese network includes several faith-based, small business, sports, student, young adult organizations in Southern California; JWI has built a national network with Marshallese community in Washington State, Arizona, Arkansas, Hawai'i and throughout California. JWI has an extensive network with Marshallese women who have had a decade health related partnership with PIHP Islanders. Marshallese are well known for their weaving and storytelling, this

would be an element of knowledge that could be successfully integrated into the development of culturally tailored materials. JWI will also assist in recruiting to the PILI 'Ohana program.

Kutturan Chamoru Foundation (KCF),. http://kutturanchamoru.org. KCF is a Chamorro cultural group with intergeneration families from Guam, Northern Mariana Islands, provides Chamorro language, music, college assistance and scholarship workshops; performs traditional Chamorro performances not only at PIF OC, but also throughout California and across the Pacific in Guam, plans for participation in upcoming Pacific Arts Festival in Guam in 2016. In addition to collaborating on the development of Chamoru Heart Truth materials, outreach and education, the KCF co-director is a producer for internet radio station that outreach NHPI communities across U.S. and the Pacific, adding to our outreach education campaign. As an active performance group KCF could develop a series of dances and storytelling around the red dress and Heart Truth campaigns.

CAL-Islanders Humanitarian Association (CIHA) --. cal-islanders.org. Founded in 1994 CIHA is dedicated to meeting the humanitarian needs of medical referral patients from Guam and other surrounding Mariana Islands who are in transient in Southern California major medical centers. With 24% of deaths due to heart disease among Chamorro and Guamanians in Orange County, CIHA will provide critical information and access to women who need to navigate the health care system under the health policies in place for citizens of US territories. In addition to contributing to the development of Chamorro language materials, culturally tailored programming, and recruitment to PILI 'Ohana.

DESCRIBE HOW YOU WILL EDUCATE AND EQUIP YOUR PARTNERS TO PROVIDE "TRAIN THE TRAINERS" PROGRAMS:

Building on the KPO project and training curriculum, we will train 12 female community leaders (2 from each community partner). Training will take place at the PHIP offices or at a community center of the partner's choosing.

We will conduct one 4 hour training session with all the trainers. Brief one hour follow-up sessions will occur two days prior to the festivals and prior to the implementation of the KPO programs. We will also integrate the Healthy Heart Handbook for women with the KPO materials. We will add new information to our conversations with the trainers as each community develops their native language materials. PIHP will provide the curriculum, materials, promotion items, tool kits for community outreach activities.

Project personnel will debrief with all trainers after a community session. Post-training evaluation provides valuable information on the areas where increased support is required and how we might more effectively use our program.

WHAT DO YOU ANTICIPATE WILL BE DIFFERENT AS A RESULT OF THE EVENTS AND ACTIVITIES CONDUCTED BY YOU AND YOUR COMMUNITY PARTNERS?

There is a paucity of research and heart health programming for NHPI living on the US continent there are multiple points of entry for NHPI to engage knowledge and practical action around Heart Truth programming. We anticipate that the greatest difference will be how our communities produce their own knowledge and engagement with Heart Truth materials and practices. Community production of Heart Truth materials creates symbols and meaning systems that facilitates NHPI community engagement with both knowledge of heart health and provide strategies to engage in

conversations with their physicians and be more conscious of heart healthy choices. For individual women who participate in the KPO program, their knowledge and skills at maintaining heart healthy activities will be greatly enhanced, importantly they will have the skills to take that knowledge to share with community members who have not participated in Heart Truth programs. By developing both trainers and NHPI students the collaborative is strengthening the infrastructure of the community that would sustain the program after the grant year. We foresee building on the

Navigating Pacific Hearts project by collaborating with a clinic to enhance early screening for heart risk.

DESCRIBE THE METHODS THAT YOU AND YOUR COMMUNITY PARTNERS WILL USE TO ASSESS ACHIEVEMENT OF YOUR PROGRAM OBJECTIVES:

We will conduct two levels of evaluation. The process evaluation we will assess our collaborations with the community; the development of Pacific Heart Truth materials, the Train the Trainer program, and process of outreach to the community. We are interested in how collaboration with the community was successful in creating a sustainable infrastructure to continue developing heart healthy programing. The outcome evaluation will assess the success of the project in increasing knowledge about heart disease, risk factors, and increased screening. We will conduct pre- and post- test evaluations at festivals where women speak with a trainer and specifically during the KPO program. For participants in the KPO program we will collect BMI, and Blood Pressure to determine actual decreases in heart disease risk. The Heart Truth pre- and post-questions will include questions regarding screening use, conversations with physicians about heart health, and questions about increased physical activity, and weight management.

COLLABORATING ORGANIZATIONS:

- Empowering Pacific Islander Communities (EPIC) partners with PIHP, provides civic engagement, advocacy, policy, youth leadership development activities for young NHPI adults, NHPI demographic "Community of Contracts" dissemination launches in Washington DC, Hawai`i, Sacramento, Los Angeles and Orange County. EPIC will assist in recruiting professional NHPI women between the ages of 25-50. They will also be instrumental in gathering demographic information about NHPI in Orange and Riverside Counties, thus enhancing our knowledge about our target audience.

The following organizations will partner with our primary organizations. The groups listed below are smaller and would greatly benefit by learning about the Heart Truth program and how they can partner with FNIH in the future. They will also strengthen the sustainability and reach of the Heart Truth program. We have listed the additional organization and the organization with whom they will partner.

- Tongan American Youth Foundation (TAYF), Tongan youth group, Inglewood, LA County partners with Famili Pe Taha;

- Mainland Council, Association of Hawaiian Civic Clubs,-- partners with `Āinahau, along with Halau Lani Ola, Hawai`i Daughters Guild, `Ahahui Lili`uokalani Hawaiian Civic Club, Ka Ha Panoa Hawaiian Civic Club; Kama`aina Club of Orange County;

- RiYakuu Softball, Marshallese Christian Center partners with Juan Wot Iakwe

- AGAPE, faith-based group, SPICA South Pacific Islander Cultural Assn., CSUF, partners with SAYOC